## Slide 1
Mid-term evaluation of the
Interreg A NEXT Poland – Ukraine programme
Conclusions and recommendations
Synthesis of conclusions and specific recommendations
EGO s.c. • June 2026

## Slide 2
KEY CONCLUSION 1
The programme architecture is coherent — clarifying changes are needed, not an overhaul
The Programme, Programme Manual, and competition documentation are, at the strategic level, consistent with the logic of the intervention; the system of project evaluation and selection criteria functions as intended.
Changes are necessary at the level of operational provisions, whose current structure generates interpretive discrepancies, information gaps, and an imbalance of burdens.
The rationale behind the recommendations is to bridge the gap between the well-designed architecture and the operational details where dysfunctions that reduce implementation effectiveness are revealed.
EGO s.c. • Evaluation of Interreg NEXT Poland–Ukraine 2021–2027
2

## Slide 3
KEY CONCLUSION 2
Four groups of modifications to programme documents
Programme Manual — clarifying the operationalization of horizontal principles (practical WCAG verification tools) and equal opportunity provisions in the context of armed conflict.
Indicator metrics in the future perspective — clear definition of eligibility criteria for what actions (in terms of scale and quality) count toward the indicator, and introduction of typologies where the indicator aggregates heterogeneous products (to capture knowledge about what the programme actually produces).
Information and communication process — a consolidated feedback channel after calls for proposals and working translations of key SPF documents in PL and UA.
Ancillary programme acts — fuller use of the RCP mandate and an information package on the asymmetry of the registration procedure on the Ukrainian side.
EGO s.c. • Evaluation of Interreg NEXT Poland–Ukraine 2021–2027
3

## Slide 4
KEY CONCLUSION 3
The 2028–2034 outlook: three structurally significant changes
Performance-Based Approach (P-BA) — each declared indicator becomes a financial commitment.
Tightening of the decommitment rule from N+3 to N+1 — reducing the programme's time buffer.
Off-the-shelf unit cost catalogs developed by the EC — a significant simplification, but with the risk of misalignment with the specific nature of cross-border cooperation. This risk is mitigated by the fact that the programme may choose to develop its own methodology for estimating rates
In this context, the report recommends a series of changes at the level of the programme implementation system.
P-BA
indicator = financial commitment
N+3 → N+1
shorter time buffer
EGO s.c. • Evaluation of Interreg NEXT Poland–Ukraine 2021–2027
4

## Slide 5
KEY CONCLUSION 4
Four directions of necessary systemic changes
Financial mechanisms — maintaining advance payments as a boundary condition, diagnosis of financial liquidity of projects and introduction of adjustments to the advance payment system, analysis of the adequacy of flat rates, milestones — negotiating with the EC a pro-rata payment mechanism (for partial achievement of targets) and a risk margin.
Competence infrastructure — RCPs as the “operational arm” of the Joint Secretariat and solutions to reduce the fragility of the single-person model on the UA side.
IT system — completing the CST2021 modernization (currency conversions, flat-rate calculations, “diff” function, UA localization) before the first call for proposals.
Monitoring — targeted diagnosis of signals: decline in the share of Ukrainian NGOs in the SPF and liquidity issues on the Ukrainian side.
EGO s.c. • Evaluation of Interreg NEXT Poland–Ukraine 2021–2027
5

## Slide 6
PART II
Specific recommendations
20 recommendations (R1–R20) across 7 thematic areas — each with justification, intended audience, and timeframe.
Implementation system · Financial mechanisms · Small Project Funds · Partnerships and horizontal principles · Communication and support · Indicator system · Ukrainian specifics

## Slide 7
PROGRAMME IMPLEMENTATION SYSTEM
R1
Strengthen the feedback system for applicants
EXPECTED EFFECTS AND JUSTIFICATION
Supplementing the existing feedback mechanism (the evaluation grid provided to each applicant) with a consolidated channel — an anonymous synthesis of the most frequently recurring weaknesses in applications published after the call — may reduce the proportion of “average/poor” ratings among rejected applicants. This is complemented by maintaining and promoting wrap-up meetings conducted by the JS for first-time applicants.
INTENDED AUDIENCE
Managing Authority and Joint Secretariat
TIMEFRAME
Future financial perspective
EGO s.c. • Evaluation of Interreg NEXT Poland–Ukraine 2021–2027
7

## Slide 8
PROGRAMME IMPLEMENTATION SYSTEM
R2
Maintaining a flexible expenditure reporting system
EXPECTED EFFECTS AND JUSTIFICATION
The current flexible system supports the financial liquidity of the programme (reimbursement from the EC) and beneficiaries (faster disbursement of tranches) and is consistent with the planned results-based payment (P-BA) logic for 2028+. In parallel — monitoring the workload of national auditors and potential funding of additional positions from technical assistance.
INTENDED AUDIENCE
MA; consultation with national auditors and JS
TIMEFRAME
Future financial perspective
EGO s.c. • Evaluation of Interreg NEXT Poland–Ukraine 2021–2027
8

## Slide 9
PROGRAMME IMPLEMENTATION SYSTEM
R3
CST2021 system modernization to bridge the implementation gap
EXPECTED EFFECTS AND JUSTIFICATION
The implementation of the package of changes will eliminate the paradox of “simplifications that do not simplify”: it will shorten payment request processing, reduce corrections, and lower barriers for Ukrainian partners (36.4% positive ratings vs 68.2% for Polish partners). Three phases: critical changes (EUR exchange rates, flat-rate calculations, “diff”), high priority, UA localization.
INTENDED AUDIENCE
MFiRP (product owner) with the CST2021 team
TIMEFRAME
Phase I within 12 months; localization before 2028+ call
EGO s.c. • Evaluation of Interreg NEXT Poland–Ukraine 2021–2027
9

## Slide 10
SIMPLIFICATIONS AND FINANCIAL MECHANISMS
R4
Assessment of personnel costs and consideration of differentiated flat rates
EXPECTED EFFECTS AND JUSTIFICATION
The 6% flat rate in regular projects (with grant values from EUR 200,000 to EUR 2.5 million) is among the lowest of comparable programmes, and 45% of beneficiaries assess the rates as barely viable or too low. During the programming of the new perspective, an analysis of actual personnel costs should be conducted, broken down by project tiers based on budget. The study may cover a sample of projects (with access to accounting records) or rely on labor cost simulations. Based on the results, a decision should be made on whether the uniform rate requires differentiation or an alternative (unit rates).
INTENDED AUDIENCE
Managing Authority (programming of the new perspective)
TIMEFRAME
Before the launch of the 2028+ perspective
EGO s.c. • Evaluation of Interreg NEXT Poland–Ukraine 2021–2027
10

## Slide 11
SIMPLIFICATIONS AND FINANCIAL MECHANISMS
R5
Maintaining the advance payment system as a boundary condition of the programme
EXPECTED EFFECTS AND JUSTIFICATION
Advance payments distinguish this programme among Interreg programmes, which are dominated by the reimbursement model. CAWI survey data confirm that they serve as a boundary condition for participation: 90% of Ukrainian partners rate advance payments as crucial or a necessary condition for participation (chi²=23.50; p<0.001). When designing the future perspective, the advance payment system should be maintained as a programme element. Any modifications to the advance payment mechanics (amount and structure of tranches, settlement rules) should be based on the diagnosis described in R6.
INTENDED AUDIENCE
Managing Authority and Joint Secretariat
TIMEFRAME
2028+ perspective
EGO s.c. • Evaluation of Interreg NEXT Poland–Ukraine 2021–2027
11

## Slide 12
SIMPLIFICATIONS AND FINANCIAL MECHANISMS
R6
Periodic monitoring of financial barriers and review of advance payment mechanisms
EXPECTED EFFECTS AND JUSTIFICATION
Financial liquidity is assessed significantly worse on the Ukrainian side: 39% of Ukrainian partners report problems, compared to 22% on the Polish side. The main source of difficulty is the financial situation of Ukrainian entities — they lack available own funds to cover project costs.
However, this financial fragility is compounded by programme mechanics that may exacerbate the problem (the 70% rule for advance payment settlement, the length of the verification cycle for payment requests). The recommendation advises first conducting a reliable diagnosis of the causes of liquidity problems (analysis of CST2021 system data, interviews, surveys with project managers and partners), followed by implementation of potential improvements.
INTENDED AUDIENCE
Managing Authority and Joint Secretariat
TIMEFRAME
Diagnosis within 12 months; improvements current/next perspective
EGO s.c. • Evaluation of Interreg NEXT Poland–Ukraine 2021–2027
12

## Slide 13
SMALL PROJECT FUNDS (SPF)
R7
Monitoring the composition of SPF applicants and compensatory mechanisms
EXPECTED EFFECTS AND JUSTIFICATION
The share of Ukrainian NGOs among small project applicants fell from 39% (in the previous programming period) to 17% in the first call of the current perspective. A strong explanatory hypothesis is the lack of advance payments in the SPF. The recommendation advises ongoing monitoring of SPF applicant structure. If the decline persists in subsequent calls — conduct a diagnosis of the causes, e.g., via a short survey or telephone interviews with Ukrainian NGOs that implemented small projects in the previous perspective but did not apply in the current one. If the diagnosis confirms that the barrier is the lack of advance payments, the programme may consider actions in two directions:
returning to a model where the programme authority (not the operator) manages the funds and can directly provide advance payments to implementers
regulatory safeguards for the SPF operator — creating conditions that allow the operator to provide advance payments without incurring disproportionate financial risk
INTENDED AUDIENCE
Managing Authority, SPF operators
TIMEFRAME
Monitoring ongoing; diagnosis after 2 calls (2027–2028)
EGO s.c. • Evaluation of Interreg NEXT Poland–Ukraine 2021–2027
13

## Slide 14
SMALL PROJECT FUNDS (SPF)
R8
Fix the SPF application generator before the next call for proposals
EXPECTED EFFECTS AND JUSTIFICATION
The generator used by the Carpathian Euroregion is the only element of the system rated clearly negatively (25.5% poor or very poor ratings). Repair priorities include: eliminating save errors and unintended data deletion, improving stability during longer work sessions, clearer error communication, and — if technically possible — introducing PL and UA interface versions.
INTENDED AUDIENCE
SPF operators in cooperation with the IT system provider
TIMEFRAME
Before the next SPF call for proposals
EGO s.c. • Evaluation of Interreg NEXT Poland–Ukraine 2021–2027
14

## Slide 15
SMALL PROJECT FUNDS (SPF)
R9
Competition documentation and generator in national languages (PL and UA)
EXPECTED EFFECTS AND JUSTIFICATION
The requirement to work exclusively in English is a barrier for smaller SPF entities — it lengthens the application process and may discourage participation. The recommendation advises making key SPF documents (call for proposals guidelines, generator user manual) available in Polish and Ukrainian — as supplementary materials alongside the binding English version. Regardless of the decision on documentation language, consider introducing Polish- and Ukrainian-language versions of the application generator interface, which does not affect the language of the application itself but facilitates system navigation.
INTENDED AUDIENCE
Managing Authority, SPF operators
TIMEFRAME
Before the next SPF call or in the future perspective
EGO s.c. • Evaluation of Interreg NEXT Poland–Ukraine 2021–2027
15

## Slide 16
PARTNERSHIPS AND HORIZONTAL PRINCIPLES
R10
Active use of the RCP mandate to support cross-border partnerships
EXPECTED EFFECTS AND JUSTIFICATION
The current RCP mandate allows for broader involvement in building partnerships than is currently the case in practice — the aim is better utilization of the existing mandate, not its expansion. Three actions: matchmaking meetings before calls, a series of thematic webinars, individual support for project concepts.
INTENDED AUDIENCE
MA with Regional Contact Points and JS
TIMEFRAME
RCPs ready by end of 2026; full launch before 2028+ call
EGO s.c. • Evaluation of Interreg NEXT Poland–Ukraine 2021–2027
16

## Slide 17
PARTNERSHIPS AND HORIZONTAL PRINCIPLES
R11
Expand wrap-up meetings with a component for first-time applicants
EXPECTED EFFECTS AND JUSTIFICATION
Some first-time applicants do not take advantage of training before submitting their application. Strengthening the existing meeting format with a regular introductory component (programme rules, common errors, partnership structure) — without creating a separate track — increases the accessibility of knowledge without the risk of unequal treatment.
INTENDED AUDIENCE
Joint Secretariat with SPF operators and RCPs
TIMEFRAME
Future financial perspective
EGO s.c. • Evaluation of Interreg NEXT Poland–Ukraine 2021–2027
17

## Slide 18
PARTNERSHIPS AND HORIZONTAL PRINCIPLES
R12
Adapting digital accessibility requirements (WCAG) to the programme specifics
EXPECTED EFFECTS AND JUSTIFICATION
The current WCAG 2.0 requirements are difficult to verify in practice — resulting in the formal acceptance of declarations without actual verification. Three actions: simplified guidelines with examples and free tools, a central audit service from technical assistance, clear definition of mandatory and recommended elements.
INTENDED AUDIENCE
MA with digital accessibility experts
TIMEFRAME
Guidelines 2026; central audit service by end of 2026
EGO s.c. • Evaluation of Interreg NEXT Poland–Ukraine 2021–2027
18

## Slide 19
COMMUNICATION, INFORMATION, SUPPORT
R13
“Two-person” solutions on the Ukrainian side
EXPECTED EFFECTS AND JUSTIFICATION
Ukrainian RCPs operate as single-person units, and availability in wartime conditions is fragile (vacation, illness, evacuation, air raid alert). Three actions: a mandatory shared email account managed by ≥2 persons, autoresponders with alternative contact information, rotating substitutions between neighboring RCPs.
INTENDED AUDIENCE
JS branch in Lviv with RCPs and the National Authority
TIMEFRAME
Short-term — implementation within 6 months
EGO s.c. • Evaluation of Interreg NEXT Poland–Ukraine 2021–2027
19

## Slide 20
COMMUNICATION, INFORMATION, SUPPORT
R14
Working translations of SPF application documentation
EXPECTED EFFECTS AND JUSTIFICATION
The language of documentation is the strongest spontaneous demand from both sides of the programme, particularly among smaller SPF entities. While maintaining English as the legally binding language — making key SPF documents available in parallel, non-binding PL and UA versions. The decision rests with the SPF operators.
INTENDED AUDIENCE
Managing Authority, Joint Secretariat
TIMEFRAME
Next financial perspective
EGO s.c. • Evaluation of Interreg NEXT Poland–Ukraine 2021–2027
20

## Slide 21
COMMUNICATION, INFORMATION, SUPPORT
R15
Workshop-style training for applicants prior to the first call for proposals
EXPECTED EFFECTS AND JUSTIFICATION
51.5% of rejected applicants are first-time applicants, and 34% of SPF applicants report information gaps during the application stage. A series of hands-on workshops (min. 3 sessions, in PL and UA, with remote participation) with system-neutral content will increase first-time applicants' chances of submitting a better-prepared application.
INTENDED AUDIENCE
Joint Secretariat with RCPs and SPF operators
TIMEFRAME
First cycle by end of 2026; integration — 2028+
EGO s.c. • Evaluation of Interreg NEXT Poland–Ukraine 2021–2027
21

## Slide 22
COMMUNICATION, INFORMATION, SUPPORT
R16
Add procedural tutorials to the YouTube channel
EXPECTED EFFECTS AND JUSTIFICATION
There is a lack of a systematic set of procedural tutorials (logging in, filling out the budget, application validation, indicator reporting). A series of short videos (5–10 min) in PL and UA versions, technology-neutral, embedded on the programme website and YouTube channel — as reference material, not promotional.
INTENDED AUDIENCE
JS (production); RCPs (distribution)
TIMEFRAME
Full package before 2028+ calls for proposals
EGO s.c. • Evaluation of Interreg NEXT Poland–Ukraine 2021–2027
22

## Slide 23
INDICATOR SYSTEM
R17
Incorporating lessons from the current perspective in designing indicator metrics
EXPECTED EFFECTS AND JUSTIFICATION
The analysis revealed two issues in the design of certain metrics that reduce data quality collected by the indicator. The first is the lack of eligibility criteria — the metrics do not define which actions count toward the indicator. The result is reporting under the same code of actions of incomparable scale and quality. The second is excessive aggregation without typology — the indicator covers qualitatively different products, but the metrics do not require their differentiation. The result is a loss of information about what the programme actually produces. The recommendation advises eliminating these issues in the future by clearly defining eligibility criteria for the indicator and introducing a typology of products where the indicator allows for diversity.
INTENDED AUDIENCE
Managing Authority and Joint Secretariat
TIMEFRAME
Designing the 2028+ indicator system
EGO s.c. • Evaluation of Interreg NEXT Poland–Ukraine 2021–2027
23

## Slide 24
INDICATOR SYSTEM
R18
Mechanisms for flexible indicator settlement taking into account the UA context
EXPECTED EFFECTS AND JUSTIFICATION
The performance-based approach (P-BA) transforms indicators into an accounting tool; combined with the N+1 rule and binary risk (no payment if the indicator is not met), this threatens loss of part of the financing programme's funding or avoidance of ambitious projects. Accordingly, in the future perspective milestones should be designed to enable phased and partial indicator settlement, and a risk margin should be negotiated with the EC — the assumption that not all interventions need to be fully successful for the programme to settle a given milestone. Second, payout values assigned to milestones should be estimated based on data from 77 current projects, taking into account inflation, cost differences between Poland and Ukraine, and differences between project types.
INTENDED AUDIENCE
MA and the Working Group for the Interreg PL–UA 2028–2034 Plan
TIMEFRAME
Programming 2028+ and negotiations with the EC
EGO s.c. • Evaluation of Interreg NEXT Poland–Ukraine 2021–2027
24

## Slide 25
INDICATOR SYSTEM
R19
Supplementing Communication Strategy monitoring with call data and baseline values
EXPECTED EFFECTS AND JUSTIFICATION
The Communication Strategy's outcome indicators essentially measure reach and exposure, not the effectiveness of communication activities. Additionally, the target values of current indicators lack a clear methodology or baseline values. The recommendation proposes using data from calls for proposals (percentage of new applicants, geographic diversity, source of knowledge about the call) as an approximate measure of communication effectiveness. It also advises establishing baseline values for reach indicators that the Communication Strategy already measures.
INTENDED AUDIENCE
Joint Secretariat (communication monitoring)
TIMEFRAME
Designing the future programme's communication strategy
EGO s.c. • Evaluation of Interreg NEXT Poland–Ukraine 2021–2027
25

## Slide 26
UKRAINIAN SPECIFICS
R20
Information package for Polish and Ukrainian partners
EXPECTED EFFECTS AND JUSTIFICATION
56.9% of Polish beneficiaries are unable to assess the registration procedure on the Ukrainian side. A dual-track package (for UA partners — early preparation of documents for the SCMU; for PL partners — description of stages and typical duration of the procedure) does not eliminate the gap but makes it predictable.
INTENDED AUDIENCE
JS with the Lviv Branch and the National Authority in Kyiv
TIMEFRAME
Short-term — development and distribution in 2026
EGO s.c. • Evaluation of Interreg NEXT Poland–Ukraine 2021–2027
26

## Slide 27
Thank you
EGO s.c. • Evaluation of the Interreg NEXT Poland–Ukraine 2021–2027 programme